About the Company

CERTIFY Health (“CERTIFY” or the “Company”) is a leading healthcare technology company that streamlines and unifies patient experience, practice and patient management, revenue cycle management and billing, and interoperability across all major electronic health record systems and laboratories.  By connecting patient experience, practice operations, and payer processes on a singular platform, CERTIFY helps hospitals, clinics, health systems, and multi-site enterprises run more efficiently, increase practice revenue, and improve patient satisfaction.

For more information, visit www.certifyhealth.com.

Background

Earlier this year, CERTIFY Health secured a Series A equity investment from growth equity firm ABS Capital Partners.  The investment from, and partnership with, ABS Capital will support the continued advancement of CERTIFY’s technology platform as well as broaden the Company’s market reach.  CERTIFY intends to expand its customer base in the middle market – an area historically untapped and less familiar in terms of the competitive landscape.

CERTIFY is seeking student partners to perform phase 1 of a (potential) two phase project.  Phase 1 is rooted in Market and Competitor Research and Data Analysis; while Phase 2 (most likely a continuation into the Summer Clinics) will be Automating Data Collection and Analysis.  It is important to keep in mind that Phase 1 will set the stage for Phase 2, and thus the template created as part of phase 1 needs to ensure consistent data gathering in perpetuity with the potential to ultimately apply an agent to automate the data collection process.

Both phases of the project will include engagement with the executive team at CERTIFY, as well as the investment team from ABS Capital Partners.  The project also provides an opportunity to better understand what it is like to work for a PE-backed portfolio company by helping to support the executive team with the execution of strategic initiatives that will drive growth and create value for investors.

Project Scope – Phase 1

- Gain understanding of CERTIFY Health’s current markets, product offerings, customers, and business model.  In collaboration with CERTIFY, work to:

  - Define the “middle market” by revenue, practice size, region, etc;

  - Develop hypotheses around growth drivers, adoption barriers, key segments (ie. outpatient clinics, behavioral health, specialty practices)

- Determine data/metrics to collect and KPIs to analyze, including but not limited to:

| DATA | KPIs |
| --- | --- |
| Market/Macro data | Market penetration |
| Competitor Products/Features | Annual Recurring Revenue/Average Contract Value (ACV) |
| Pricing/Contract models | Growth / Churn rates |
| Funding Rounds/Valuations | Customer Acquisition Costs (CAC) |

- Map competitive landscape and benchmark featured offerings, by:

  - Identifying direct and adjacent competitors and extracting product features, pricing models, differentiators, etc.

  - Building a competitor matrix by gathering quantitative data (market shares, funding, clients) and then validating with qualitative sources (interviews, analyst commentary)

  - Utilizing marketing, PR, social media materials and mentions to gain insights into competitive set evolvement and potential “next steps”

- Run comparative analysis and generate market insights by:

  - Calculating and determining growth rates, feature overlap, pricing vs. value insights

  - Using tools like regression, cluster analysis, market share modeling to identify gaps in the market, underserved segments, white spaces ripe for expansion

- Produce visuals, charts, and dashboards to help prioritize strategic moves and execution, clearly explaining which segments to target first, what kinds of tactics (ie. Pricing) to utilize, new product advancements to prioritize, etc.

Expected Deliverables

- Excel dashboard containing data and analysis

- PowerPoint presentation clearly illustrating results, recommendations for next steps, and summary of resources and tools utilized

Anticipated Timeline and Time Commitment

- Week 1: Team formation, initial scoping, and research; first client meeting [client presentation on Company background, platform, market overview, competition, etc.], first faculty advisor meeting; 15-20 hours

- Weeks 2-3: Data gathering, preliminary analysis; client meetings (weekly); faculty advisor meetings (weekly); 40 hours (over 2 weeks)

- Week 4: Draft findings, complete stress tests, seek advisor/client feedback; midpoint check-in with client to ensure on track and within scope of work and expectations; weekly advisor meeting; 20 hours

- Week 5: Refine models and analysis, begin to build executive deck and draft presentation scripts; 20 hours

- Week 6: Intensive Prep Weekend (virtual); Practice presentation and finalize scripts; Present to client; 20 hours

Scheduled Meetings [TO BE CONFIRMED]

- Client Kick-Off Call, both teams, Monday, January 5, 2026, 9am-10am ET

- Weekly Client Meetings, Team #1, Mondays, January 12-February 2, 2026, 9am-9:30am ET

- Weekly Client Meetings, Team #2, Mondays, January 12-February 2, 2026, 9:30am-10am ET

- Final Presentations, both teams, Thursday, February 12, 2026, 12pm-1:30pm

Advisors

Kim Kile, Georgetown University, Senior Career Advisor, Executive in Residence for Private Equity; Winter Clinics Faculty Partner

Kevon Kothari, CERTIFY Health, CEO

Keith ODonnell, CERTIFY Health, CFO

Josh Troop, CERTIFY Health, CMO

Cal Wheaton, ABS Capital Partners, General Partner