# CERTIFY INTEL

Competitive Intelligence Platform

COMPREHENSIVE PROJECT PLAN

Phases 2-5: January 19 - February 7, 2026

| Document Version | 1.0 |
| --- | --- |
| Date Prepared | January 18, 2026 |
| Prepared By | Certify Health Team 1 |
| Client | Certify Health |
| Project Duration | January 5 - February 7, 2026 |
| Document Status | Final |

# 1. EXECUTIVE SUMMARY

Certify Intel is an AI-powered competitive intelligence platform developed to address Certify Health's critical need for comprehensive, real-time monitoring of the healthcare IT competitive landscape. This document outlines the complete project plan for Phases 2 through 5, building upon the technical foundation established in Phase 1.

## Project Overview

Client: Certify Health (Healthcare IT Solutions Provider)

Project Name: Certify Intel - Competitive Intelligence Platform

Total Duration: January 5, 2026 - February 7, 2026 (34 days)

Remaining Phases: 4 (Phases 2-5)

Team Size: 5 members

Current Status: Phase 1 Complete (100%)

## Key Metrics Achieved in Phase 1

| Metric | Target | Achieved |
| --- | --- | --- |
| Competitors Tracked | 50+ | 87 |
| Data Points per Competitor | 32 | 32 |
| Automated Tests | 100% Pass | 19/19 (100%) |
| API Endpoints | 10+ | 20+ |
| AI Integration | GPT-4 | GPT-4 + Chatbox |

# 2. PROJECT BACKGROUND AND PROBLEM STATEMENT

## 2.1 Business Context

Certify Health operates in the highly competitive middle-market healthcare IT sector, providing patient engagement and healthcare check-in solutions. The company faces significant challenges in maintaining awareness of competitive movements, market trends, and emerging threats within their target market segment.

## 2.2 Problem Statement

Prior to this project, Certify Health lacked a systematic approach to competitive intelligence. Key challenges included:

Manual, time-intensive competitor research processes requiring 40+ hours per month

Inconsistent data collection methodologies leading to gaps in competitive knowledge

Delayed awareness of critical competitive movements (funding rounds, product launches, acquisitions)

No centralized repository for competitive data, resulting in siloed information

Inability to generate actionable insights from disparate data sources

Limited visibility into pricing strategies and market positioning of competitors

## 2.3 Stakeholders

Executive Leadership: Strategic decision-making based on competitive insights

Sales Team: Battlecards and competitive positioning for deal support

Product Team: Feature gap analysis and roadmap prioritization

Marketing Team: Messaging differentiation and market positioning

## 2.4 Project Constraints

Timeline: 34-day development window with fixed end date (February 7, 2026)

Budget: Minimal external API costs; leverage free-tier services where possible

Technical: Must integrate with existing Excel-based workflows

Data: Reliance on publicly available information; no access to proprietary databases

# 3. SOLUTION OVERVIEW AND ARCHITECTURE

## 3.1 Solution Description

Certify Intel is a comprehensive competitive intelligence platform that automates the collection, analysis, and presentation of competitor data. The solution combines web scraping, AI-powered data extraction, and intuitive visualization to transform raw competitive information into actionable strategic insights.

## 3.2 Core Components

Web Dashboard: 8+ specialized views providing real-time access to competitive intelligence

AI Executive Summary: GPT-4 powered analysis with interactive chatbox for follow-up queries

Data Collection Engine: Automated web scraping using Playwright for reliable extraction

News Monitoring: Multi-source aggregation with 90-day historical coverage

Excel Integration: Full data export with Power Query compatibility

Alert System: Configurable email notifications for critical competitive movements

## 3.3 Technology Stack

| Layer | Technology |
| --- | --- |
| Backend Framework | FastAPI (Python) |
| Database | SQLite |
| Web Scraping | Playwright |
| AI/ML | OpenAI GPT-4 |
| Frontend | HTML5, CSS3, JavaScript |
| Data Export | OpenPyXL, JSON |
| News APIs | Google News RSS, NewsAPI.org |
| Task Queue | Celery (optional) |

# 4. CURRENT STATE: PHASE 1 COMPLETION SUMMARY

## 4.1 Phase 1 Overview

Phase 1 focused on establishing the complete technical foundation for the Certify Intel platform. This phase has been completed ahead of schedule, with all technical deliverables exceeding original requirements.

Phase 1 Duration: January 5-18, 2026

Status: 100% COMPLETE

## 4.2 Deliverables Completed

Backend API Server: 20+ REST endpoints for data access, export, and AI features

Database Schema: 87 competitors with 32 data points per record

Web Dashboard: 8-page responsive dashboard with navigation and visualization

AI Integration: GPT-4 executive summary with interactive chatbox

Battlecard Generator: Automated sales enablement battlecard generation

Comparison Tool: Side-by-side competitor comparison with gap analysis

Analytics Engine: Threat distribution, market share, and pricing visualizations

Export System: Excel and JSON export APIs for Power Query integration

News Monitoring: 3-month historical news aggregation from multiple sources

Test Suite: 19 automated tests with 100% pass rate

## 4.3 Challenges Encountered and Resolutions

| Challenge | Root Cause | Resolution |
| --- | --- | --- |
| API Method Mismatch | Discovery endpoint required POST instead of GET | Updated frontend and test suite to use correct HTTP method |
| Missing Scraper Method | Main.py called non-existent scrape() method | Added scrape() alias to CompetitorScraper class |
| Response Format Inconsistency | Change log API returned incorrect structure | Standardized to object with "changes" key |
| AI Chat Dependency | Chatbox non-functional without API key | Implemented graceful fallback with configuration guidance |

# 5. TEAM ROSTER AND RESPONSIBILITIES

| Role | Team Member | Primary Responsibilities |
| --- | --- | --- |
| Team Lead / Coordinator | Andrew Kimelman | Cross-team coordination, client communication, approvals, strategic direction |
| Product Development Lead | Connor Hickey | Backend development, AI integration, technical architecture, bug fixes |
| Research Lead | Kevin Way | Competitive landscape mapping, data sourcing, validation, research methodology |
| Data Lead | Connor Maloney | Excel dashboard, data quality, KPIs, data standardization |
| Delivery Lead | Mo Srouji | Documentation, presentations, visual design, user experience |

# 6. PHASE 2: DATA VALIDATION AND QUALITY ASSURANCE

Duration: January 19-24, 2026 (6 days)

Objective: Ensure all 87 competitors have accurate, complete, and verified data.

## 6.1 Phase 2 Tasks (25 Tasks)

| # | Task | Assigned To | Completion Criteria |
| --- | --- | --- | --- |
| 1 | Create data validation dashboard view | Connor Hickey | Dashboard displays completeness % for all fields |
| 2 | Implement bulk data correction API | Connor Hickey | API accepts CSV and updates multiple records |
| 3 | Add data quality scoring algorithm | Connor Hickey | Each competitor receives 0-100 quality score |
| 4 | Create automated freshness checker | Connor Hickey | System flags records not updated in 30+ days |
| 5 | Build change history tracking | Connor Hickey | Audit log captures who/what/when for edits |
| 6 | Review competitor qualification criteria | Andrew Kimelman | Signed-off document defining valid competitors |
| 7 | Validate competitor batch 1 (67-87) | Andrew Kimelman | Each competitor reviewed, errors corrected |
| 8 | Establish data quality standards | Andrew Kimelman | Written standards with minimum quality scores |
| 9 | Conduct mid-phase review meeting | Andrew Kimelman | Meeting minutes with decisions and actions |
| 10 | Approve final data quality report | Andrew Kimelman | Signed approval on data quality summary |
| 11 | Validate competitor batch 2 (1-22) | Kevin Way | Each competitor website reviewed for accuracy |
| 12 | Document data sources for 32 fields | Kevin Way | Source documentation with URLs for each field |
| 13 | Identify 10 additional competitors | Kevin Way | List of 10 new competitors with preliminary data |
| 14 | Create source reliability ratings | Kevin Way | Each data source rated 1-5 for reliability |
| 15 | Cross-reference funding data | Kevin Way | Funding amounts verified with discrepancies logged |
| 16 | Validate competitor batch 3 (23-44) | Connor Maloney | Each competitor reviewed for completeness |
| 17 | Create completeness report by category | Connor Maloney | Excel report showing completeness by category |
| 18 | Standardize all pricing formats | Connor Maloney | All pricing in consistent format |
| 19 | Normalize numeric values | Connor Maloney | All numbers in consistent units |
| 20 | Build validation checklist template | Connor Maloney | Reusable checklist for data quality |
| 21 | Validate competitor batch 4 (45-66) | Mo Srouji | Each competitor reviewed for visual issues |
| 22 | Document UI/UX issues found | Mo Srouji | Issue log with screenshots |
| 23 | Create validation status mockup | Mo Srouji | Visual design for quality tracking view |
| 24 | Design quality report template | Mo Srouji | Professional template for quality documents |
| 25 | Prepare Phase 2 summary presentation | Mo Srouji | 10-slide deck summarizing Phase 2 |

## 6.2 Phase 2 Completion Criteria

All 87 competitors manually reviewed by at least one team member

Data quality score averages 80% or higher across all competitors

All critical data errors corrected and verified

Source documentation exists for all 32 data fields

Data quality report reviewed and approved by Team Lead

Phase 2 completion presentation delivered

# 7. PHASE 3: BUSINESS INTELLIGENCE AND INSIGHTS

Duration: January 25-28, 2026 (4 days)

Objective: Transform validated data into actionable business insights for client stakeholders.

## 7.1 Phase 3 Tasks (25 Tasks)

| # | Task | Assigned To | Completion Criteria |
| --- | --- | --- | --- |
| 1 | Create custom report generation API | Connor Hickey | API generates PDF reports with parameters |
| 2 | Build trend analysis visualization | Connor Hickey | Chart showing competitor metrics over time |
| 3 | Implement SWOT analysis generator | Connor Hickey | Automated SWOT based on competitor data |
| 4 | Add market segment filtering | Connor Hickey | Analytics filterable by market segment |
| 5 | Create positioning matrix chart | Connor Hickey | Scatter plot: price vs. features |
| 6 | Define strategic analysis priorities | Andrew Kimelman | Top 5 strategic questions documented |
| 7 | Write executive summary for client | Andrew Kimelman | 2-page executive summary of insights |
| 8 | Review and approve all analyses | Andrew Kimelman | Signed approval on each analysis |
| 9 | Prepare Executive Workshop content | Andrew Kimelman | Workshop materials and talking points |
| 10 | Lead stakeholder alignment meeting | Andrew Kimelman | Meeting minutes with feedback |
| 11 | Write comprehensive threat report | Kevin Way | 5-page report on top 10 threats |
| 12 | Create competitive landscape map | Kevin Way | Visual map of competitor positioning |
| 13 | Document competitive differentiators | Kevin Way | Analysis of unique value propositions |
| 14 | Research market trend predictions | Kevin Way | Report on emerging market trends |
| 15 | Compile news sentiment summary | Kevin Way | Summary of 3-month sentiment patterns |
| 16 | Create pricing intelligence matrix | Connor Maloney | Comprehensive pricing comparison |
| 17 | Build feature comparison scorecard | Connor Maloney | Weighted feature scoring for top 20 |
| 18 | Calculate market share estimates | Connor Maloney | Market share % based on customer data |
| 19 | Create KPI tracking dashboard data | Connor Maloney | Data feeds for key performance indicators |
| 20 | Develop competitive benchmarks | Connor Maloney | Benchmark metrics vs. competitors |
| 21 | Design threat analysis visualization | Mo Srouji | Professional visual for threat report |
| 22 | Create market positioning infographic | Mo Srouji | Single-page infographic |
| 23 | Build presentation template | Mo Srouji | Branded template for presentations |
| 24 | Design competitive one-pager | Mo Srouji | Single-page summary of insights |
| 25 | Prepare Executive Workshop slides | Mo Srouji | Complete slide deck for Jan 27 |

## 7.2 Phase 3 Completion Criteria

Threat analysis report completed and approved

Pricing intelligence matrix covers all 87 competitors

Executive presentation materials ready for Jan 27 workshop

All visualizations reviewed and approved

Competitive positioning matrix displaying correctly

SWOT analysis available for top 20 competitors

# 8. PHASE 4: DOCUMENTATION AND TRAINING MATERIALS

Duration: January 29 - February 2, 2026 (5 days)

Objective: Create comprehensive documentation enabling client self-sufficiency.

## 8.1 Phase 4 Tasks (25 Tasks)

| # | Task | Assigned To | Completion Criteria |
| --- | --- | --- | --- |
| 1 | Create API documentation with examples | Connor Hickey | Complete API reference for all endpoints |
| 2 | Record video walkthrough of dashboard | Connor Hickey | 15-minute screen recording of features |
| 3 | Write technical troubleshooting guide | Connor Hickey | Common errors with solutions |
| 4 | Create backup and restore procedures | Connor Hickey | Step-by-step backup guide |
| 5 | Document system architecture | Connor Hickey | Architecture doc with dependencies |
| 6 | Review and approve all documentation | Andrew Kimelman | Signed approval on each document |
| 7 | Define documentation standards | Andrew Kimelman | Style guide for all documentation |
| 8 | Conduct documentation review meeting | Andrew Kimelman | Meeting with team to review drafts |
| 9 | Create project governance document | Andrew Kimelman | Roles, responsibilities, escalation |
| 10 | Approve training material curriculum | Andrew Kimelman | Signed training plan |
| 11 | Write FAQ document (30+ questions) | Kevin Way | FAQ with detailed answers |
| 12 | Create research methodology guide | Kevin Way | Guide for adding new competitors |
| 13 | Document data source update procedures | Kevin Way | Guide for refreshing data sources |
| 14 | Write CI best practices document | Kevin Way | Best practices for ongoing CI |
| 15 | Create glossary of terms | Kevin Way | Comprehensive glossary |
| 16 | Write complete data dictionary | Connor Maloney | All 32 fields defined with examples |
| 17 | Create Excel template usage guide | Connor Maloney | Guide for Excel exports |
| 18 | Document data quality procedures | Connor Maloney | Ongoing data quality monitoring |
| 19 | Write competitor update procedure | Connor Maloney | Guide for adding/editing competitors |
| 20 | Create data validation checklist | Connor Maloney | Reusable validation checklist |
| 21 | Write user guide for dashboard | Mo Srouji | Comprehensive guide with screenshots |
| 22 | Create quick reference card | Mo Srouji | Single-page cheat sheet |
| 23 | Design documentation templates | Mo Srouji | Branded templates for all docs |
| 24 | Write feature reference guide | Mo Srouji | Detailed guide for each feature |
| 25 | Create onboarding checklist | Mo Srouji | Checklist for new users |

## 8.2 Phase 4 Completion Criteria

User guide completed with screenshots for all 8 pages

API documentation covers all 20+ endpoints

Video walkthrough recorded and reviewed

FAQ document contains 30+ questions and answers

Data dictionary defines all 32 fields

All documentation approved by Team Lead

# 9. PHASE 5: CLIENT PRESENTATION AND HANDOFF

Duration: February 3-7, 2026 (5 days)

Objective: Deliver polished presentation and ensure smooth handoff to client.

## 9.1 Phase 5 Tasks (25 Tasks)

| # | Task | Assigned To | Completion Criteria |
| --- | --- | --- | --- |
| 1 | Finalize all bug fixes | Connor Hickey | Zero critical/high bugs remaining |
| 2 | Create production deployment checklist | Connor Hickey | Step-by-step deployment guide |
| 3 | Record live demo backup video | Connor Hickey | Pre-recorded demo for backup |
| 4 | Prepare system handoff package | Connor Hickey | Complete code and config package |
| 5 | Conduct technical handoff session | Connor Hickey | Technical walkthrough with client IT |
| 6 | Lead final client presentation | Andrew Kimelman | 30-minute executive presentation delivered |
| 7 | Conduct project retrospective | Andrew Kimelman | Lessons learned documented |
| 8 | Obtain client sign-off | Andrew Kimelman | Signed acceptance of deliverables |
| 9 | Present at Clinics Weekend | Andrew Kimelman | Successful Feb 6-8 presentation |
| 10 | Deliver final project report | Andrew Kimelman | Complete project summary |
| 11 | Conduct final data accuracy audit | Kevin Way | Audit confirms 90%+ accuracy |
| 12 | Prepare Q&A response document | Kevin Way | 50+ anticipated questions with answers |
| 13 | Create monitoring handoff guide | Kevin Way | Guide for ongoing CI activities |
| 14 | Document research methodology | Kevin Way | Complete methodology documentation |
| 15 | Present research findings | Kevin Way | Research summary presentation |
| 16 | Build final Excel dashboard | Connor Maloney | Excel with 87 competitors, charts, formulas |
| 17 | Create Excel user instructions | Connor Maloney | Guide for Excel features |
| 18 | Verify all Excel formulas | Connor Maloney | All formulas tested and verified |
| 19 | Export final data backup | Connor Maloney | Complete data export in multiple formats |
| 20 | Create data maintenance schedule | Connor Maloney | Calendar of refresh activities |
| 21 | Design executive presentation deck | Mo Srouji | 20-slide branded presentation |
| 22 | Create demo script | Mo Srouji | Written script for live demo |
| 23 | Prepare printed handoff materials | Mo Srouji | Printed copies of key docs |
| 24 | Design project summary one-pager | Mo Srouji | Single-page project summary |
| 25 | Coordinate presentation logistics | Mo Srouji | All logistics confirmed and tested |

## 9.2 Phase 5 Completion Criteria

Client presentation delivered successfully

All documentation delivered and accepted

Excel dashboard completed with all visualizations

Client sign-off obtained on all deliverables

Technical handoff completed with client IT team

Project retrospective documented

Clinics Intensive Weekend presentation completed

# 10. FINAL DELIVERABLES

## 10.1 Web Application

A fully functional, cloud-ready web application providing:

Real-time competitive intelligence dashboard with 8+ specialized views

AI-powered executive summary using GPT-4 with interactive chatbox

Battlecard generation for sales enablement

Side-by-side competitor comparison tool

Analytics visualizations (threat distribution, market share, pricing)

Market positioning map with bubble chart visualization

Change log with filtering by company and date

Full data export (Excel, JSON) for Power Query integration

News monitoring with 3-month historical coverage

Configurable alert system for critical competitive movements

## 10.2 Excel Dashboard

A comprehensive Excel workbook containing all competitive intelligence data:

Complete export of all 87 competitors with 32 data points each

Multi-sheet workbook: Overview, Competitors, Pricing, Features, Analytics

Interactive pivot tables for data analysis and filtering

Professional charts: Bar charts, pie charts, scatter plots, trend lines

Conditional formatting: High=Red, Medium=Yellow, Low=Green

Formula-driven calculations for market share, scores, rankings

Data validation dropdowns for standardized entry

ALL INPUT CELLS AND HARDCODED VALUES DISPLAYED IN BLUE FONT

Print-ready formatting for executive reporting

Power Query connections to web application API

## 10.3 Documentation Package

User Guide: Step-by-step instructions for all dashboard features

API Documentation: Technical reference for all endpoints

Data Dictionary: Definitions for all 32 data fields

FAQ Document: 30+ frequently asked questions and answers

Quick Reference Card: One-page summary of common tasks

Training Materials: Onboarding checklists and video walkthroughs

Technical Documentation: Architecture, dependencies, troubleshooting

## 10.4 Ongoing Support

30-day warranty period for bug fixes and critical issues

Knowledge transfer sessions with client team

Documentation for self-service maintenance

Recommended schedule for data refresh activities

# 11. KEY DATES AND MILESTONES

| Date | Milestone | Status |
| --- | --- | --- |
| January 5, 2026 | Project Start | Complete |
| January 18, 2026 | Phase 1 Complete | Complete |
| January 24, 2026 | Phase 2 Complete | Scheduled |
| January 27, 2026 | Executive Presentation Workshop | Scheduled |
| January 28, 2026 | Phase 3 Complete | Scheduled |
| February 2, 2026 | Phase 4 Complete | Scheduled |
| February 6-8, 2026 | Clinics Intensive Weekend | Scheduled |
| February 7, 2026 | Phase 5 Complete / Project End | Scheduled |
| February 7, 2026 | Final Client Delivery | Scheduled |

END OF DOCUMENT